## NYIRAMUHEBE-KANZOGERA-MUYUNZWE
FOREWORD
1 | SITE PRELIMINARIES
2 | SUPPLY AND LAYING OF PIPES
3 | CIVIL WORKS
4 | REHABILITATION WORKS
NYIRAMUHEBE-KANZOGERA-MUYUNZWE DRINKING WATER SUPPLY SYSTEM IN KINIHIRA SECTOR OF RUHANGO DISTRICT (Total Length 10.94km with 2.68Km Extension)
Detailed Quantity Estimate
Item N° | DESCRIPTION | UNIT | QTY | RATE | AMOUNT
1 | SITE PRELIMINARIES
1.1 | Preparation of the site according to technical specifications;acces road, mobilization of the material and its transport on the site, installation of the site, storage, guarding, including the toilet of the personnel. The installation includes the water connection on the existing network. Site preparation also includes, site clearance, removal of top soil, levelling or any shaping necessary to the installations of the site together with all the cut and fill necessary to this end. The estimated cost for this item is maintained all through to the completion of the works. | LS | 1 |  | 0
1.2 | Putting in place a site billboards according to the client's instructions, and including and all accruals | Ls | 3 |  | 0
1.3 | Design review and production of work execution documents, and including all accruals, and as built plans documents (soft and hard copies) | Km | 10.94 |  | 0
| SUBTOTAL DIVISION 1: |  |  |  | 0
2 | Supply and installation of pipelines
The following prices include :
2.1 | The earthwork, trenches backfilling and land remediation at natural surface ground.
2.2 | Supply, fix, and pressure testing for watertightness of pipes PN16 including lubricants and seals.
2.1 | Earthwork by excavation and backfilling
2.1.1 | Excavation and backfilling of Trenche with 1 x0.6 m (according to Wasac standard) depth , including all accruals. | lm | 10936.66 |  | 0
2.1.2 | Supply and Installation of Concrete Terminals (painted blue and numbered) on the route of the pipeline, dim.0.15 * 0.15 * 0.8m , every 100m and at each change of direction (elbow position) | Item | 109.3666 |  | 0
| SUBTOTAL 2.1: |  |  |  | 0
2.2 | Supply and installation of pipelines
2.2.1 | HDPE Pipe ND 75 NP 16 | lm | 1633.4 |  | 0
2.2.2 | HDPE Pipe ND 63 NP 16 | lm | 410.4 |  | 0
2.2.3 | HDPE Pipe ND 50 NP 16 | lm | 589.8 |  | 0
2.2.4 | HDPE Pipe ND 40 NP 16 | lm | 2807.9 |  | 0
2.2.5 | HDPE Pipe ND 32 NP 16 | lm | 5160.4 |  | 0
2.2.6 | HDPE Pipe ND 40 NP 25 | lm | 334.76 |  | 0
2.2.8 | casing with GS 1 1/4'' pipe | lm | 19 |  | 0
2.2.9 | Casing with G.S 2 1/2" pipes | lm | 88.24 |  | 0
2.2.10 | Solid mass of masonry in stones for pipes stabilization | m3 | 5.25 |  | 0
2.2.11 | Pressure test | lm | 10936.66 |  | 0
2.2.12 | Desinfection of network with chlorine | lm | 10936.66 |  | 0
| SUBTOTAL 2.2: |  |  |  | 0
| SUBTOTAL DIVISION 2: |  |  |  | 0
3 | CIVIL WORKS
3.1 | INSPECTION CHAMBERS
3.1.1 | Air vent #(1.6×1.6×1.2m)(Located Nyamirambo village, Muyunzwe cell)
3.1.1.1 | Earthworks cut, fill and evacuation or overlay of the surplus soils, including all accruals | m3 | 9.45 |  | 0
3.1.1.2 | Hardcore (stones pitching) of 30 cm with a filling of 1:10 cement sand mortar mix, saturated with water | m3 | 1.26 |  | 0
3.1.1.3 | Blind concrete 1:3:6 Cement Sand Aggregate, thickness 5 cm | m3 | 0.21 |  | 0
3.1.1.4 | Reinforced concrete for base slab ,1:2:4 Cement Sand Aggregate | m3 | 0.5103 |  | 0
3.1.1.5 | Reinforced concrete for roof slab ,1:2:4 Cement Sand Aggregate | m3 | 0.4536 |  | 0
3.1.1.6 | Walls in stones masonry jointed with a mortar of 1:4 Cement Sand Mix | m3 | 1.4112 |  | 0
3.1.1.7 | Coating of the internal face of wall of the inspection chamber with 3 layers of plaster of 300 kg/m3 | m2 | 6.048 |  | 0
3.1.1.8 | Plaster on the upper side of roof slab with a rough mortar of 1:4 Cement Sand Mix | m2 | 3.024 |  | 0
3.1.1.9 | Supply and fix the damp proof course between the roof slab, the wall and the beam of support | m2 | 1.344 |  | 0
3.1.1.10 | Supply and fix of the metallic cover of 60X60X0.3 cm with a ventilation shaft at the top and mosquito screen | item | 1 |  | 0
3.1.1.11 | Supply and fix an iron ladder for interior access embedded in the wall, painted with 3 layers of paint "rust preventive", the step=25cm | lm | 3.6 |  | 0
3.1.1.12 | Supply and installation of hydraulic equipment and Fittings for connection of Air release valve | LS | 1 |  | 0
| SUBTOTAL |  |  |  | 0
| SUBTOTAL of 1 Air vent |  | 1 |  | 0
3.1.2 | Washout #(1.6×1.6×1.2m)( All located in Nyamirambo village, Muyunzwe cell)
3.1.2.1 | Earthworks cut, fill and evacuation or overlay of the surplus soils, including all accruals | m3 | 9.45 |  | 0
3.1.2.2 | Hardcore (stones pitching) of 30 cm with a filling of 1:10 cement sand mortar mix, saturated with water | m3 | 1.26 |  | 0
3.1.2.3 | Blind concrete 1:3:6 Cement Sand Aggregate, thickness 5 cm | m3 | 0.21 |  | 0
3.1.2.4 | Reinforced concrete for base slab ,1:2:4 Cement Sand Aggregate | m3 | 0.5103 |  | 0
3.1.2.5 | Reinforced concrete for roof slab ,1:2:4 Cement Sand Aggregate | m3 | 0.4536 |  | 0
3.1.2.6 | Walls in stones masonry jointed with a mortar of 1:4 Cement Sand Mix | m3 | 1.4112 |  | 0
3.1.2.7 | Coating of the internal face of wall of the inspection chamber with 3 layers of plaster of 300 kg | m2 | 6.048 |  | 0
3.1.2.8 | Plaster on the upper side of roof slab with a rough mortar of 1:2 Cement Sand Mix | m2 | 3.024 |  | 0
3.1.2.9 | Supply and fix the damp proof course between the roof slab, the wall and the beam of support | m2 | 1.344 |  | 0
3.1.2.10 | Supply and fix of the metallic cover of 60X60X0.3 cm with a ventilation shaft at the top and mosquito screen | item | 1 |  | 0
3.1.2.11 | Supply and fix an iron ladder for interior access embedded in the wall, painted with 3 layers of paint "rust preventive", the step=25cm | lm | 1.6 |  | 0
3.1.2.12 | Supply and installation of hydraulic equipment and Fittings for connection of washout | LS | 1 |  | 0
3.1.2.13 | Rejection works | Ls | 1 |  | 0
| SUBTOTAL |  |  |  | 0
| SUBTOTAL of 2 Washout |  | 2 |  | 0
3.1.3 | CONSTRUCTION OF SECTION VALVE BRANCHES CHAMBERS # (1.8×1.8×1.2m) (Located in Gasharu, Nyarubumbiro, Nyamirambo, Muyunzwe, Ruhuha,and Gasiza villages)
3.1.3.1 | Terracing, digging, cutting, excavation, backfilling, overlay of surplus soil and land remediation, including all acruals | m3 | 8.232 |  | 0
3.1.3.2 | Hardcore (stones pitching) of 20 cm with a filling of 1:10 cement sand mortar mix, saturated with water | m3 | 1.3074 |  | 0
3.1.3.3 | Blind concrete 1:3:6 Cement Sand Aggregate, thickness 5 cm | m3 | 0.1779 |  | 0
3.1.3.4 | Reinforced concrete for base slab and roof slab ,1:2:4 Cement Sand Aggregate | m3 | 0.5337 |  | 0
3.1.3.5 | Lateral walls in stones masonry jointed with a mortar of 1:4 Cement Sand Mix | m3 | 1.4112 |  | 0
3.1.3.6 | Coating of the internal side of wall of the inspection chamber with plaster of 300 kg/m3 ciment mixture | m2 | 6.048 |  | 0
3.1.3.7 | Plaster on upper side of the slab with a rough mortar of 1:2 Cement Sand Mix | m2 | 3.024 |  | 0
3.1.3.8 | Supply and fix the damp proof course between the roof slab, the wall and the beam of support | m2 | 1.176 |  | 0
3.1.3.9 | Supply and fix of the metallic cover of 60X60X0.3 cm with a ventilation shaft at the top and the mosquito screen | item | 1 |  | 0
3.1.3.10 | Supply and fix an iron ladder for interior access embedded in the wall, painted with 3 layers of rust preventive paint, the step=25cm | lm | 1 |  | 0
3.1.3.11 | Supply and installation of hydraulic equipment and Fittings for connection of automatic valve chamber (All valve of PN16). | LS | 1 |  | 0
| SUBTOTAL 3.1.3 |  |  |  | 0
| SUBTOTAL 3.1.3 (For 9 Valve chamber) |  | 9 |  | 0
3.1.4 | CONSTRUCTION OF BREAK PRESSURE CHAMBER # (2.4×1.6×1.2m)
3.1.4.1 | Terracing, digging, cutting, excavation, backfilling, overlay of surplus soil and land remediation, including all acruals | m3 | 6.4974 |  | 0
3.1.4.2 | Hardcore (stones pitching) of 30 cm with voids full with cement and sand mortar mix of ratio 1 to 10 respectively, saturated with water | m3 | 1.7514 |  | 0
3.1.4.3 | Blind concrete 1:3:6 Cement Sand Aggregate, thickness 5 cm | m3 | 0.2919 |  | 0
3.1.4.4 | Reinforced concrete for base slab ,1:2:4 Cement Sand Aggregate | m3 | 0.7308 |  | 0
3.1.4.5 | Reinforced concrete for roof slab ,1:2:4 Cement Sand Aggregate | m3 | 0.6804 |  | 0
3.1.4.6 | Walling with stonework | m3 | 2.3604 |  | 0
3.1.4.7 | Coating of the internal face of wall of the tank with 3 hydrafuges water proofing coats | m2 | 4.116 |  | 0
3.1.4.8 | Coating of the internal side of wall of the inspection chamber with 3 layers of plaster of 300 kg/m3 ciment mixture | m2 | 4.116 |  | 0
3.1.4.9 | Supply and coating the faces of the tank with 3 layers of "sikalatex" paint | m2 | 4.116 |  | 0
3.1.4.10 | Plaster on the upper side of roof slab with a rough mortar 1:2 Cement Sand | m2 | 4.536 |  | 0
3.1.4.11 | Supply and fix damp proof course between the roof slab, the wall and the beam of support | m2 | 2.142 |  | 0
3.1.4.12 | Supply and fix of the metallic cover of 60 x 60 x 0.3cm with a ventilation shaft at the top and a mosquito screen | item | 1 |  | 0
3.1.4.13 | Supply a portable aluminium ladder, the step=25cm and total length = 3 meter. | LS | 1 |  | 0
3.1.4.14 | Supply and installation of hydraulic equipment and Fittings for connection of break pressure | LS | 1 |  | 0
| SUBTOTAL 3.1.4 |  |  |  | 0
| SUBTOTAL 3.1.4 (For 2 BREAK PRESSURE) |  | 2 |  | 0
3.1.5 | Construction of Ph regulation chamber 2.8mx2.2mx1.75m , external dimensions( Refer to designs)
3.1.5.1 | Terracing, digging, cutting, excavation, backfilling, overlay of surplus soil and land remediation, including all accruals and site clearing after construction | m3 | 10.4462 |  | 0
3.1.5.2 | Hardcore (stones pitching) of 20 cm with a filling of 1:10 cement sand mortar mix, saturated with water | m3 | 2.0076 |  | 0
3.1.5.3 | Blind concrete 1:3:6 Cement Sand Aggregate, thickness 5 cm | m3 | 0.50189 |  | 0
3.1.5.4 | Reinforced concrete for base slab and roof slab ,1:2:4 Cement Sand Aggregate | m3 | 3.0114 |  | 0
3.1.5.5 | Lateral walls in stones masonry jointed with a mortar of 1:4 Cement Sand Mix | m3 | 3.5538 |  | 0
3.1.5.6 | Internal walls in in stones masonry jointed with a mortar of 1:4 Cement Sand Mix | m3 | 1.352 |  | 0
3.1.5.7 | Coating of the internal side of wall of the inspection chamber with 3 layers of plaster of 300 kg cement mixture | m2 | 13.6 |  | 0
3.1.5.8 | Plaster on upper side of the slab with a rough mortar of 1:2 Cement Sand Mix | m2 | 4.68 |  | 0
3.1.5.9 | Supply and fix damp proof course between the roof slab, the wall and the beam of support | m2 | 1.2 |  | 0
3.1.5.10 | Supply and fix of the metallic cover of 60X60X0.3 cm with a ventilation shaft at the top and the mosquito screen | LS | 3 |  | 0
3.1.5.11 | Supply and fix an noncorrosive ladder for interior access embedded in the wall, painted with 3 layers of rust preventive paint, the step=25cm | LS | 2 |  | 0
3.1.5.12 | Supply and installation of hydraulic equipment | LS | 1 |  | 0
3.1.5.13 | Supply and Testing Calcite material (ex-limestone/travertine or dolomite) | LS | 1 |  | 0
3.1.5.14 | Supply of fine sand for the filtration chamber | LS | 1 |  | 0
3.1.5.15 | Supply of aggregate for the filtration chamber | LS | 1 |  | 0
3.1.5.16 | pH regulator testing and water quality testing for each water tanks and at least for each water tap served by one water tank | LS | 1 |  | 0
| SUBTOTAL 3.1.5 |  |  |  | 0
| S/Total PH regulator |  | 1 |  | 0
| SUBTOTAL 3.1.5 (For 2pH Regulators) |  | 2 |  | 0
3.1.6 | Water quality testing
3.1.6.1 | Physical parameters: Colour, Turbidity, Temperature, pH, Conductivity, Total Hardness (CaCO3), Total Alkalinity (CaCo3),Total Suspended Solids (TSS), Total Dissolved Solids (TDS) | LS | 1 |  | 0
3.1.6.2 | Chemical parameters: Calcium (Ca2+), Magnesium (Mg2+), Sodium ( Na+), Potassium (K+), Iron (Fe2+), Bicarbonates (HCO3-) Sulfates (SO42-), Chlorides (Cl-), Nitrate (NO3), Nitrites (NO2- ) Phosphates (PO4 3-), Ammonium (NH4+), Fluorides (F-)
3.1.6.3 | Trace elements: Aluminium (Al), Antimony (Sb), Cyanide (HCN – CN), Iron (Fe), Lead (Pb), Manganese (Mn), Mercury (Hg), Copper(Cu), Arsenic (As)
3.1.6.4 | - Bacteriological elements: Total Coliforms, E. Coli and Faecal Coliform
| S/Total |  |  |  | 0
| Sub total 3.1 |  |  |  | 0
3.2 | RESERVOIRS
3.2.1 | Construction of 25 m3 capacity reservoir
3.2.1.1 | Terracing, digging, cutting, excavation, backfilling, overlay of surplus soil and land remediation, including all acruals | m3 | 44.3625 |  | 0
3.2.1.2 | Hardcore (stones pitching) of 30 cm with voids full with cement and sand mortar mix of ratio 1 to 10 respectively, saturated with water | m3 | 8.038 |  | 0
3.2.1.3 | Blind concrete 1:3:6 Cement Sand Aggregate, thickness 5 cm | m3 | 1.3397 |  | 0
3.2.1.4 | Hydraulic reinforced concrete for the base | m3 | 5.0193 |  | 0
3.2.1.5 | Reinforced concrete for roof slab,columns and beams ,1:2:4 Cement Sand Aggregate | m3 | 3.1433 |  | 0
3.2.1.6 | Walling with shapened hardcore, fair face and pointing in joints | m3 | 16.4868 |  | 0
3.2.1.7 | Coating of the internal face of wall of the tank with 3 hydrafuges water proofing coats | m2 | 32.8053 |  | 0
3.2.1.8 | Supply and coating the faces of the tank with 3 layers of "Sikalatex" paint | m2 | 32.8053 |  | 0
3.2.1.9 | Plaster on the upper side of roof slab with a rough mortar 1:2 Cement Sand | m2 | 20.955 |  | 0
3.2.1.10 | Supply and fix damp proof course between the roof slab, the wall and the beam of support | m2 | 8.0817 |  | 0
3.2.1.11 | Supply and fix of the metallic cover of 80X80X0.3 cm with a ventilation shaft at the top and a mosquito screen | Item | 2 |  | 0
3.2.1.12 | Supply a portable aluminium ladder, the step=25cm and total length = 3 meter. | LS | 2 |  | 0
INSPECTION CHAMBER
3.2.1.13 | Terracing, digging, cutting, excavation, backfilling, overlay of surplus soil and land remediation, including all acruals | m3 | 9.1875 |  | 0
3.2.1.14 | Hardcore (stones pitching) of 20 cm with a filling of 1:10 cement sand mortar mix, saturated with water | m3 | 0.24058 |  | 0
3.2.1.15 | Blind concrete 1:3:6 Cement Sand Aggregate, thickness 5 cm | m3 | 0.19845 |  | 0
3.2.1.16 | Reinforced concrete for base slab and roof slab ,1:2:4 Cement Sand Aggregate | m3 | 0.3969 |  | 0
3.2.1.17 | Lateral walls in stones masonry jointed with a mortar of 1:3 Cement Sand | m3 | 1.281 |  | 0
3.2.1.18 | Coating of the internal side of wall of the inspection chamber with 3 layers of plaster of 300 kg ciment mixture | m2 | 9.912 |  | 0
3.2.1.19 | Plaster on upper side of the slab with a rough mortar 1:2 Cement Sand | m2 | 3.549 |  | 0
3.2.1.20 | Supply and fix damp proof course between the roof slab, the wall and the beam of support | m2 | 1.323 |  | 0
3.2.1.21 | Supply and fix of the metallic cover of 60X60X0.3 cm with a ventilation shaft at the top and the mosquito screen | Item | 1 |  | 0
3.2.1.22 | Supply and fix an iron ladder for interior access embedded in the wall, painted with 3 layers of paint "rust preventive", the step=25cm | lm | 1 |  | 0
3.2.1.23 | Supply and installation of DI flanged hydraulic equipment and Fittings for connection of 25m3 reservoir | LS | 1 |  | 0
REJECTION WORK # (1.45×1.5×1m)
3.2.1.24 | Terracing, digging, cutting, excavation, backfilling, overlay of surplus soil and land remediation, including all acruals | m3 | 6.2842 |  | 0
3.2.1.25 | Hardcore (stones pitching) of 20 cm with voids full with cement and sand mortar mix of ratio 1 to 10 respectively, saturated with water | m3 | 0.462 |  | 0
3.2.1.26 | Blind concrete 1:3:6 Cement Sand Aggregate, thickness 5 cm | m3 | 0.12127 |  | 0
3.2.1.27 | Hydraulic reinforced concrete for the base | m3 | 0.25468 |  | 0
3.2.1.28 | Walling with fair face stones works and pointing the joint of external faces | m3 | 0.1371 |  | 0
3.2.1.29 | Coating of internal faces with plaster of 300 kg/m3 ciment mixture | m2 | 5.315 |  | 0
3.2.1.30 | Soakaway pit 1 m3, full of gravel and hardcore (stones pitching) | LS | 1 |  | 0
| SUBTOTAL 3.2.1: |  |  |  | 0
| SUBTOTAL OF 3 Res. 25m3 |  | 3 |  | 0
3.2.2 | CONSTRUCTION OF A RESERVOIR OF 10 M3 CAPACITY
3.2.2.1 | Terracing, digging, cutting, excavation, backfilling, overlay of surplus soil and land remediation, including all acruals | m3 | 31.7625 |  | 0
3.2.2.2 | Hardcore (stones pitching) of 30 cm with voids full with cement and sand mortar mix of ratio 1 to 10 respectively, saturated with water | m3 | 4.1588 |  | 0
3.2.2.3 | Blind concrete 1:3:6 Cement Sand Aggregate, thickness 5 cm | m3 | 0.69313 |  | 0
3.2.2.4 | Hydraulic reinforced concrete for the base 1:2:4 Cement Sand Aggregate | m3 | 2.3708 |  | 0
3.2.2.5 | Reinforced concrete for roof slab and beams ,1:2:4 Cement Sand Aggregate | m3 | 1.1871 |  | 0
3.2.2.6 | Walling with shapened hardcore, fair face and pointing in joints | m3 | 9.3313 |  | 0
3.2.2.7 | Coating of the internal face of wall of the tank with 3 hydrafuges water proofing coats | m2 | 19.3962 |  | 0
3.2.2.8 | Supply and coating the faces of the tank with 3 layers of "Sikalatex" paint | m2 | 19.3962 |  | 0
3.2.2.9 | Plaster on the upper side of roof slab with a rough mortar 1:2 Cement Sand | m2 | 11.8712 |  | 0
3.2.2.10 | Supply and fix damp proof course between the roof slab, the wall and the beam of support | m2 | 4.2223 |  | 0
3.2.2.11 | Supply and fix of the metallic cover of 80 x 80 x 0.3 cm with a ventilation shaft at the top and a mosquito screen | item | 1 |  | 0
3.2.2.12 | Supply and Installation of Almnium ladder (Inox ladder) for access | LS | 1 |  | 0
INSPECTION CHAMBER # (2×1.6×1m)
3.2.2.13 | Terracing, digging, cutting, excavation, backfilling, overlay of surplus soil and land remediation, including all acruals | m3 | 6.5625 |  | 0
3.2.2.14 | Hardcore (stones pitching) of 20 cm with a filling of 1:10 cement sand mortar mix, saturated with water | m3 | 0.8778 |  | 0
3.2.2.15 | Blind concrete 1:3:6 Cement Sand Aggregate, thickness 5 cm | m3 | 0.1995 |  | 0
3.2.2.16 | Reinforced concrete for base slab and roof slab ,1:2:4 Cement Sand Aggregate | m3 | 0.5712 |  | 0
3.2.2.17 | Lateral walls in stones masonry jointed with a mortar of 1:4 Cement Sand Mix | m3 | 0.756 |  | 0
3.2.2.18 | Coating of the internal side of wall of the inspection chamber with plaster of 300 kg/m3 ciment mixture | m2 | 5.88 |  | 0
3.2.2.19 | Plaster on upper side of the slab with a rough mortar of 1:2 Cement Sand Mix | m2 | 2.3468 |  | 0
3.2.2.20 | Supply and fix the damp proof course between the roof slab and the wall | m2 | 0.882 |  | 0
3.2.2.21 | Supply and fix of the metallic cover of 60X60X0.3 cm with a ventilation shaft at the top and the mosquito screen | item | 1 |  | 0
3.2.2.22 | Supply a portable aluminium ladder for interior access embedded in the wall, painted with 3 layers of rust preventive paint, the step=25cm | LS | 1 |  | 0
3.2.2.23 | Supply and installation of Flanged hydraulic equipment & Fittings and DI pipes for connection of chamber according to the client instruction | LS | 1 |  | 0
REJECTION WORK #
3.2.2.24 | Terracing, digging, cutting, excavation, backfilling, overlay of surplus soil and land remediation, including all acruals | m3 | 5.9535 |  | 0
3.2.2.25 | Hardcore (Stones pitching) of 20 cm with a filling of 1:10 cement sand mortar mix, saturated with water | m3 | 0.462 |  | 0
3.2.2.26 | Blind concrete 1:3:6 Cement Sand Aggregate, thickness 5 cm | m3 | 0.12127 |  | 0
3.2.2.27 | Reinforced concrete 1:2:4 Cement Sand Aggregate, for base slab | m3 | 0.25468 |  | 0
3.2.2.28 | Masonry walls in hardcore, with fair face pointed at the joints | m3 | 0.1371 |  | 0
3.2.2.29 | Coating of walls with plaster of 300 kg/m3 cement mixture | m2 | 5.565 |  | 0
3.2.2.30 | Soakaway pit 1 m3, full of gravel and hardcore (stones pitching) | LS | 1 |  | 0
| SUBTOTAL 3.2.2: |  |  |  | 0
| TOTAL OF 2R 10 m3 |  | 2 |  | 0
| SUBTOTAL 3.2: |  |  |  | 0
3.3 | WATER POINTS
3.3.1 | Construction of Water point with double taps for community
3.3.1.1 | Earthworks cut, fill and evacuation or overlay of the surplus soils, including all accruals | m3 | 22.512 |  | 0
3.3.1.2 | Hardcore (stones pitching) of 30 cm with a filling of 1:10 cement sand mortar mix, saturated with water | m3 | 2.1782 |  | 0
3.3.1.3 | Blind concrete 1:3:6 Cement Sand Aggregate, thickness 5 cm | m3 | 0.38119 |  | 0
3.3.1.4 | Reinforced concrete for base slab ,1:2:4 Cement Sand Aggregate | m3 | 1.1025 |  | 0
3.3.1.5 | Reinforced concrete for roof slab ,1:2:4 Cement Sand Aggregate | m3 | 0.06825 |  | 0
3.3.1.6 | walls in stones masonry jointed with a mortar of 1:3 Cement Sand | m3 | 0.97944 |  | 0
3.3.1.7 | Coating of walls with plaster of 300 kg/m3 | m2 | 13.923 |  | 0
3.3.1.8 | Plaster on the upper side of roof slab with a rough mortar of 1:3 Cement Sand | m2 | 0.105 |  | 0
3.3.1.9 | Supply and fix the damp proof course between the roof slab and the wall | m2 | 0.588 |  | 0
3.3.1.10 | Supply and fix of the metallic cover of 50X50X0.3 cm | item | 1 |  | 0
3.3.1.11 | Supply and installation of all hydraulic equipment and Fittings including volumetric water meter with at least nominal flow rate of 1.5m3/h and max admissible pressure of 16 bar | LS | 1 |  | 0
3.3.1.12 | Soakaway pit 1 m3, full of gravel and hardcore (stones pitching) | LS | 1 |  | 0
| Sub total 3.3.1: |  |  |  | 0
| Total for 10 Water taps |  | 10 |  | 0
3.3.2 | Construction of a water point with 3 taps for Schools
3.3.2.1 | Terracing, digging, cutting, excavation, backfilling, overlay of surplus soil and land remediation, including all acruals | m3 | 24 |  | 0
3.3.2.2 | Hardcore of 30 cm with a filling of cement and sand mortar 1:10 mixture, saturated with water | m3 | 2.0745 |  | 0
3.3.2.3 | Blind concrete 1:3:6 Cement Sand Aggregate, thickness 5 cm | m3 | 0.34575 |  | 0
3.3.2.4 | Reinforced concrete for base slab ,1:2:4 Cement Sand Aggregate | m3 | 1.05 |  | 0
3.3.2.5 | Reinforced concrete for roof of slab on watermeter chamber, 1:2:4 Cement Sand Aggregate | m3 | 0.09 |  | 0
3.3.2.6 | walls in stones masonry with fair face jointed with a mortar of 1:3 Cement Sand | m3 | 0.9328 |  | 0
3.3.2.7 | Coating of walls with plaster of 300 kg/m3 cement mixture | m3 | 13.26 |  | 0
3.3.2.8 | Plaster on the upper side of roof slab with a rough mortar of 1:2 Cement Sand | m2 | 0.1 |  | 0
3.3.2.9 | Supply and fix the damp proof course between the roof slab and the walls | m2 | 0.56 |  | 0
3.3.2.10 | Supply and fix of the metallic cover of 50 x 50 x 0,3 cm | item | 1 |  | 0
3.3.2.11 | Soakaway pit 1 m3, full of gravel and hardcore (stones pitching) | LS | 1 |  | 0
3.3.2.12 | Supply and installation of all hydraulic equipment and Fittings including volumetric water meter with at least nominal flow rate of 1.5m3/h and max admissible pressure of 16 bar | LS | 1 |  | 0
| Sub total 3.3.2: |  |  |  | 0
| Sub total 1 waterpoint 3 taps 3.3.2: |  | 2 |  | 0
3.3.3 | Construction of the Kiosk with double taps
3.3.3.1 | Preliminary works
| Cutting and filling for leveling | m3 | 30.1392 |  | 0
3.3.3.2 | Foundation
| Excavation | m3 | 8.652 |  | 0
| Blind concrete | m3 | 0.6489 |  | 0
| Masonry with stones for foundation | m3 | 8.652 |  | 0
| Concrete for leveling foundations | m2 | 10.815 |  | 0
| Damp proofing against humidity | lm | 4.326 |  | 0
3.3.3.3 | Masonary
| Masonry in burnt bricks with external joints pointed | m3 | 3.5009 |  | 0
| Ventilator in concrete blocks | m2 | 0.336 |  | 0
3.3.3.4 | Concrete
| Ring beam in reinforced concrete | m3 | 0.5418 |  | 0
3.3.3.5 | Roofing
| Wooden struts 100 X 50 X 5 (mm) | lm | 18 |  | 0
| Wooden purlins 40 X 40 X 3 (mm) | lm | 27.6 |  | 0
| Rafters in right angled triangle | lm | 240 |  | 0
| Facia board in wood | lm | 25.8 |  | 0
| Pile in metalic tubes 60 x 40 x 3 mm | lm | 9 |  | 0
3.3.3.6 | Cover
| Cover of tile in blue prepainted autoportant | m2 | 28.98 |  | 0
3.3.3.7 | Shutters
| Metallic simple door semi glazed with burglar proofs | item | 1 |  | 0
| Hardwood doors | item | 1 |  | 0
| Glazed Metallic window with burglar proofs 100X120 cm | item | 2 |  | 0
3.3.3.8 | Paving
| Floor with smooth finish | m2 | 14.9675 |  | 0
| Splash apron and water channel | m2 | 13.104 |  | 0
3.3.3.9 | Plastering
| Plastering of the interial walls | m2 | 38.808 |  | 0
| Plinth | lm | 8.652 |  | 0
3.3.3.10 | Ceiling to Eaves | m2 | 6.72 |  | 0
3.3.3.11 | Carten rail and box assembly | lm | 4.2 |  | 0
3.3.3.12 | Paint
| Latex paints on walls | m2 | 38.808 |  | 0
| Enamel paint | m2 | 14.61 |  | 0
| Varnish on flash or solid timber doors | m2 | 2.73 |  | 0
| Varnish on Eave ceiling | m2 | 6.72 |  | 0
3.3.3.13 | Soakaway pit 1.5 m3, full of gravel and hardcore covered by concrete slabs for the acquisition of water that has not entered in jerrycans | LS | 1 |  | 0
3.3.3.14 | Supply and installation of hydraulic equipment and Fittings including volumetric water meter with at least nominal flow rate of 1.5m3/h and max admissible pressure of 16 bar | LS | 1 |  | 0
| Sub total of BFK |  |  |  | 0
| SUBTOTAL of 1 BFK: |  | 1 |  | 0
| SUBTOTAL 3.3 of WATER POINTS: |  |  |  | 0
| SUBTOTAL DIVISION 3: |  |  |  | 0
4 | REHABILITATION WORKS
4.1 | REHABILITATION OF CATCHMENT OF SOURCES (Nyiramuhebe and Kanzogera)
4.1.1 | Site clearance, removal of top vegetable soil, and site leveling or any shaping necessary | m2 | 333.3333 |  | 0
4.1.2 | Earthwork , cut, fill and evacuation or overlay of the surplus soils, including all accruals | m3 | 151.5333 |  | 0
4.1.3 | Increase in value for a hard and rock ground | m3 | 80.51 |  | 0
4.1.4 | Supply and fix 18m PVC strainer DE90 DN80 PN10 to 20 cm of the tablecloth and routing of water in pipe PVC DE75 DN60 PN10 of the strainer to the starting chamber at 45 m, including all accruals | LS | 1 |  | 0
4.1.5 | Supply and fix rolled filitrant river gravel, well washed up to 60 cm height, including all accruals | m3 | 8.3333 |  | 0
4.1.6 | Supply and fix plastic tight sheet with the top of the gravel folded in 3 layers, including all accruals | m2 | 21.3333 |  | 0
4.1.7 | Fill with clay for a tight layer of 30 cm | m3 | 3.8333 |  | 0
4.1.8 | Fill with fine grained soil to a layer of 15 cm on top of the clay, including all accruals | m3 | 3.6233 |  | 0
4.1.9 | Fill with soils without roots and other organic matter by compacting each time layers of 20 cm up to the level of the original ground, including all accruals | m3 | 232.0433 |  | 0
4.1.10 | Excavate a trench of protection of the source up to 80 cm depth. The bottom width 40 cm, including all accruals. | m3 | 16 |  | 0
4.1.11 | Retaining Wall in Stone masonry for catchment area protection | m3 | 3 |  | 0
4.1.12 | Put in place a protective fence of quickset hedge in euphorbiums against animals, including all accruals | lm | 32.6667 |  | 0
4.1.13 | Plant passparum around the zone of harnessing, including all accruals | m2 | 233.3333 |  | 0
| Sub Total |  |  |  | 0
| SUBTOTAL of 2 sources: |  | 2 |  | 0
4.2 | REHABILITATION OF STARTING AND COLLECTION CHAMBERS
4.2.1 | Earthwork by cut, fill and evacuation or overlay of the surplus soils, including all accruals | m3 | 20 |  | 0
4.2.2 | Stripping or removal of old internal face of wall of chamber and external joints | m2 | 24 |  | 0
4.2.3 | Repointing of external face of walls | m2 | 25.92 |  | 0
4.2.4 | Coating of the internal face of wall of the chamber with 3 hydrafuges water proofing coats | m2 | 24.14 |  | 0
4.2.5 | application of sikalatex later on internal surface after the impermeability test of the chamber | m2 | 24.14 |  | 0
4.2.6 | Supply and coating some external parts(cover,hydraulic connectios,..) of the chamber with 3 layers of "Epoxy" paint | m2 | 4.9 |  | 0
4.2.7 | Plaster on the upper side of roof slab with a rough mortar 1:2 Cement Sand | m2 | 21.64 |  | 0
4.2.8 | Supply and fix of the metallic cover of 60X60X0.3 cm | item | 2 |  | 0
4.2.9 | Supply and fix hydraulic equipements | ls | 2 |  | 0
| S/ T |  |  |  | 0
| SUBTOTAL of 2 STARTING CHAMBERS: |  | 2 |  | 0
4.3 | Partial rehabilitation of chamber (Valve ,Washout and Air vent ) (Located in Muyunzwe, Nyamirambo villages)
4.3.1 | Earthworks cut, fill and evacuation or overlay of the surplus soils, including all accruals | m3 | 32.4 |  | 0
4.3.2 | Stripping or removal of old internal face of wall of chamber and external joints | m3 | 41.97 |  | 0
4.3.3 | Repointing of external face of walls | lm | 24.33 |  | 0
4.3.4 | Coating of the internal face of wall of the chamber with 3 hydrafuges water proofing coats | m2 | 20.73 |  | 0
4.3.5 | Plaster on the upper side of roof slab with a rough mortar 1:2 Cement Sand | m2 | 14.58 |  | 0
4.3.6 | Supply and fix of the metallic cover of 60X60X0.3 cm | item | 1 |  | 0
4.3.7 | Supply and fix hydraulic equipements | LS | 1 |  | 0
| S/ T |  |  |  | 0
| SUBTOTAL of 5 CHAMBERS: |  | 5 |  | 0
4.4 | Partial Rehabilitation of Public tap stand
4.4.1 | Stripping or removal of old face of wall | m2 | 4 |  | 0
4.4.2 | Coating of walls with 3 layers of plaster of 1:2 Cement Sand | m2 | 5.07 |  | 0
4.4.3 | construction of valve chamber for the tap | LS | 1 |  | 0
4.4.4 | Soakaway pit 1 m3, full of gravel and hardcore (stones pitching) | item | 1 |  | 0
4.4.5 | Supply and fix hydraulic equipements including water meter | LS | 1 |  | 0
| S/ T |  |  |  | 0
| SUBTOTAL of 6Taps: |  | 6 |  | 0
| SUBTOTAL DIVISION 4: |  |  |  | 0
| GRAND TOTAL |  |  |  | 0
| VAT(18%) |  |  |  | 0
| GRAND TOTAL( TAX INCLUSIVE) |  |  |  | 0